1. Pick any one feature from an app you use daily (for example: 'Search Restaurants' in Zomato or 'Add to Cart' in Flipkart) and break down the testing tasks for this feature using a Work Breakdown Structure (WBS) — list at least 6 distinct testing activities or sub-tasks.

Answer:

A Work Breakdown Structure (WBS) divides a large testing job into smaller, manageable tasks. The feature chosen here is 'Add to Cart' in Flipkart. The testing work is broken down as follows:

| WBS No. | Testing Activity | Sub-tasks |
| --- | --- | --- |
| 1.1 | Requirement Analysis & Test Planning | Study the Add to Cart requirements, identify the scope, and prepare the test plan. |
| 1.2 | Test Scenario & Test Case Design | Write test cases for adding one item, multiple items, the same item twice, changing quantity, and size/colour variants. |
| 1.3 | Test Data & Environment Setup | Prepare test accounts, in-stock and out-of-stock products, and the required devices and browsers. |
| 1.4 | Functional Testing | Verify that the product is added, the cart count updates, and the price and quantity are correct for guest and logged-in users. |
| 1.5 | UI & Usability Testing | Check the button states, success messages, cart icon badge, and layout on different screen sizes. |
| 1.6 | Compatibility Testing | Run the tests on Android, iOS, Chrome, and Firefox. |
| 1.7 | Integration Testing | Verify that the cart works correctly with the wishlist, discounts, and checkout. |
| 1.8 | Performance Testing | Check the response time of Add to Cart during sale-time traffic. |
| 1.9 | Defect Reporting & Retesting | Log defects with clear steps and screenshots, then retest the fixes. |
| 1.10 | Regression Testing | Re-run existing cart and checkout tests to confirm nothing else is broken. |
| 1.11 | Test Reporting & Closure | Prepare the test summary report and get sign-off. |

2. For the 'Send Message' feature in WhatsApp, estimate the total test effort required by listing all the main test activities, assigning estimated hours to each, and calculating the overall effort needed.

Answer:

The effort for the WhatsApp 'Send Message' feature is estimated activity by activity, and the hours are then added together with a small buffer:

| No. | Test Activity | Details | Est. Hours |
| --- | --- | --- | --- |
| 1 | Requirement Analysis & Test Planning | Study the feature and plan the test approach | 4 |
| 2 | Test Scenario & Test Case Design | Text, emoji, long text, media, group chat, delivery ticks | 12 |
| 3 | Test Data & Environment Setup | Devices, accounts, network conditions | 6 |
| 4 | Functional Test Execution | Send text, media and group messages, offline sending, ticks | 16 |
| 5 | Non-Functional Testing | Performance, security sanity, usability, compatibility | 10 |
| 6 | Defect Reporting | Log and track defects | 6 |
| 7 | Defect Retesting | Verify the fixed defects | 4 |
| 8 | Regression Testing | Re-run existing chat tests | 8 |
| 9 | Test Reporting & Closure | Summary report and sign-off | 3 |
|  | Subtotal |  | 69 |
|  | Contingency (10%) | Buffer for delays and rework | 7 |
|  | Total Effort |  | 76 |

Overall Effort: The total estimated effort is 69 + 7 = 76 hours, which is about 9.5 person-days at 8 hours per day.

3. Given the following scenario: Flipkart's 'Apply Coupon' feature is being released as a small module. Using the steps of test effort estimation discussed in class, create a simple estimation sheet (table) showing each test activity, estimated hours, and any assumptions you make.

Answer:

Steps followed: understand the scope, list the activities, estimate each, note assumptions, add a buffer, and total it.

| No. | Test Activity | Est. Hours | Assumptions |
| --- | --- | --- | --- |
| 1 | Requirement Review & Test Planning | 2 | Coupon rules (validity, minimum cart value, usage limit) are stable. |
| 2 | Test Case Design | 5 | About 30 test cases at roughly 10 minutes each. |
| 3 | Test Data & Environment Setup | 2 | Backend team provides test coupons (valid, expired, used, below minimum). |
| 4 | Functional Test Execution | 6 | 30 test cases at about 12 minutes each, one full cycle. |
| 5 | UI & Compatibility Checks | 3 | 2 mobile platforms and 2 browsers. |
| 6 | Integration Checks | 3 | Cart, checkout and payment modules already work. |
| 7 | Defect Reporting & Retesting | 4 | About 8 defects at roughly 30 minutes each. |
| 8 | Regression Testing | 3 | An existing cart/checkout smoke suite of about 15 test cases. |
| 9 | Test Reporting & Closure | 1 | Standard test summary report. |
|  | Subtotal | 29 |  |

4. Read about Test Point Analysis (TPA) as introduced in class. In your own words, explain how TPA could help estimate testing effort for a new 'Movie Booking' feature in BookMyShow. List two advantages and one limitation of using TPA for this purpose.

Answer:

What is TPA? Test Point Analysis (TPA) estimates black-box testing effort from the size of the feature and how demanding its quality requirements are. These are converted into test points, which are then converted into hours.

How TPA helps estimate the BookMyShow Movie Booking feature:

- Size of the feature: Break the feature into functions such as search shows, select seats, apply offers, pay, and get the ticket, and measure each.

- Quality requirements: Payment security and performance during a big movie release get a high weight; usability gets a medium weight.

- Environment and productivity: Adjust for team experience, test tools, and how stable the test environment is.

- Conversion to effort: Test points become total hours, split across design, execution, and retesting.

Two Advantages:

- More objective. The estimate comes from measurable size and defined factors, not a guess.

- Covers quality attributes. It includes security and performance, which matter for a busy payment feature like BookMyShow.

One Limitation:

- Needs data and effort. It needs function point counting and past productivity data, which take time to collect, so it suits small or fast agile releases poorly.