## Defect Report
Defect ID | Test Case | Defect Summary | Reproduced Step | Test Data | Defect Types | Defect Severity | Defect Priority | Expected Result | Actual Result | Tester Name | Attachment | Status
Savaari (Android)
1 | 1 | Account - Name validation | 1) Launch Savaari app 2) Tap profile icon 3) Open Account 4) Enter a 2-letter name in NAME 5) Observe the field | Name: om | UI, Functionality | Low | Low | A valid short name (e.g. "Om") is accepted, or the minimum length rule is clearly stated. | Error shown: "Name must be more than 2 characters". Two-letter names cannot be saved. | Om | https://drive.google.com/file/d/1Jab_u05S9sdHxBMW0UL04k5iacGPCsDV/view?usp=drive_link | Assigned
2 | 10 | Account - Mobile number format | 1) Launch Savaari app 2) Tap profile icon 3) Open Account 4) Check the MOBILE field | Mobile: 919265878121 | UI | Low | Low | Mobile shown in a standard format, e.g. +91 92658 78121. | Mobile displayed as "919265878121", country code merged into the number. | Om | https://drive.google.com/file/d/1Jab_u05S9sdHxBMW0UL04k5iacGPCsDV/view?usp=drive_link | Assigned
3 | 30 | Round Trip results - Filter overlaps chip | 1) Open Outstation Cabs > Round Trip 2) Select Gandhinagar - Mumbai and a date, then search 3) Observe the filter bar above the car list | Gandhinagar - Mumbai, 06-10-2026 07:00 AM, return 07-10-2026 | UI | Medium | Medium | Filter button and all chips (Hatchback, Sedan, SUV, Innova) fully visible with no overlap. | Filter button covers the Hatchback chip, which is cut off and unreadable. | Om | https://drive.google.com/file/d/1yalB2otMzAKBGMFcQRbAZ1XiWON_FPu3/view?usp=drive_link | Assigned
4 | 40 | Local results - Filter overlaps chip | 1) Open Local tab 2) Select 12 hrs / 120 kms and Gandhinagar, then search 3) Observe the filter bar above the car list | Gandhinagar Local 12hr/120km, 06-10-2026 07:00 AM | UI | Medium | Medium | Filter button and all chips fully visible with no overlap. | Filter button covers the Hatchback chip, which is cut off and unreadable. | Om | https://drive.google.com/file/d/1kVYpyCD01axx2BXBfBOrt0IKe3d-MCo2/view?usp=drive_link | Assigned
5 | 50 | Round Trip results - Recommended badge clipped | 1) Open Outstation Cabs > Round Trip 2) Search Gandhinagar - Mumbai 3) Look at the first car card (Ertiga) | Gandhinagar - Mumbai, 06-10-2026 to 07-10-2026 | UI | Low | Low | "Recommended" badge fully visible, aligned with the card edge. | Badge text is cut off at the top where the card meets the banner above it. | Om | https://drive.google.com/file/d/1yalB2otMzAKBGMFcQRbAZ1XiWON_FPu3/view?usp=drive_link | Assigned
6 | 60 | Local results - Header text | 1) Open Local tab 2) Select 12 hrs / 120 kms 3) Search in Gandhinagar 4) Read the header on the results screen | Gandhinagar Local 12hr/120km, 06-10-2026 07:00 AM | UI | Low | Low | Clean header, e.g. "Gandhinagar - Local (12hr/120km)"; package shown once. | Header repeats "Local" and the package in nested brackets, and wraps onto two lines. | Om | https://drive.google.com/file/d/1kVYpyCD01axx2BXBfBOrt0IKe3d-MCo2/view?usp=drive_link | Assigned
7 | 70 | Local tab - Wrong tagline | 1) Launch Savaari app 2) Tap the LOCAL tab 3) Read the heading above the package selector | Package: 4 hrs / 40 kms | UI | Low | Medium | Tagline relevant to local rentals. | Tagline reads "INDIA'S PREMIER INTERCITY CABS", which is wrong for local hourly rentals. | Om | https://drive.google.com/file/d/1fKdPi5LZZfRhBxBor1URgLT6v2jn4uT4/view?usp=drive_link | Assigned
8 | 80 | Round Trip picker - Trip End | 1) Open Outstation Cabs 2) Select ROUND TRIP 3) Tap trip date/time 4) Select Wed 21 Oct, 1:00 PM 5) Check the TRIP END card | Trip start: Wed 21 Oct, 01:00 PM | UI, Functionality | Medium | High | Trip End shows a sensible return date and time, and can be chosen by the user. | TRIP END shows "Wed, 04 Nov / Wednesday" (no time, 14 days after start). Trip Start shows a time, so the two cards are inconsistent. | Om | https://drive.google.com/file/d/1J10FQgfEOyGue8aMAhcvATios5fLZwVU/view?usp=drive_link | Assigned
9 | 90 | One Way picker - Default start time | 1) Open Outstation Cabs > One Way 2) Tap trip start date/time 3) Note the pre-selected time | Tester time at capture: about 10:56 PM, 05 Oct Default: Tue 06 Oct, 12:30 AM | Functionality | Low | Medium | A sensible default start time, consistent on every tab. | Default is Tue Oct 06, 12:30 AM. | Om | https://drive.google.com/file/d/15BmuD7Akp-Fv_dz0JE1fNxS-FfhumjbO/view?usp=drive_link | Assigned
10 | 100 | Local picker - Default start time | 1) Open Local tab 2) Tap trip start date/time 3) Note the pre-selected time | Tester time at capture: about 11:00 PM, 05 Oct Default: Tue 06 Oct, 12:45 AM | Functionality | Low | Medium | Same sensible default start time as the other tabs. | Default is Tue Oct 06, 12:45 AM. | Om | https://drive.google.com/file/d/1fKdPi5LZZfRhBxBor1URgLT6v2jn4uT4/view?usp=drive_link | Assigned
11 | 110 | Airport picker - Default start time | 1) Open Airport tab 2) Tap trip start date/time 3) Note the pre-selected time | Tester time at capture: about 11:02 PM, 05 Oct Default: Tue 06 Oct, 3:45 AM | Functionality | Low | Medium | Same sensible default start time as the other tabs. | Default is Tue Oct 06, 3:45 AM. | Om | https://drive.google.com/file/d/1sYuMyJFxJEtEgmSlTXx_po7W1ug-78sT/view?usp=drive_link | Assigned
12 | 120 | One Way picker - Hour wheel | 1) Open Outstation Cabs > One Way 2) Tap trip start date/time 3) Select Tue Oct 06 4) Scroll the hour wheel | Date: Tue Oct 06, 12:30 AM | UI, Functionality | Medium | Medium | Hour wheel lists valid hours in order (12, 1, 2, 3 ...) with no leftover hours. | Hour wheel shows 10, 11, then 12 selected, and nothing below. The previous day's list may not be refreshed. | Om | https://drive.google.com/file/d/15BmuD7Akp-Fv_dz0JE1fNxS-FfhumjbO/view?usp=drive_link | Assigned
13 | 130 | Local picker - Hour wheel | 1) Open Local tab 2) Tap trip start date/time 3) Select Tue Oct 06 4) Scroll the hour wheel | Date: Tue Oct 06, 12:45 AM | UI, Functionality | Medium | Medium | Hour wheel lists valid hours in order (12, 1, 2, 3 ...) with no leftover hours. | Hour wheel shows 10, 11, then 12 selected, and nothing below. | Om | https://drive.google.com/file/d/1fKdPi5LZZfRhBxBor1URgLT6v2jn4uT4/view?usp=drive_link | Assigned